## Slide 1: How to Fix a Troubled Project
Tapping the brakes on that rolling dumpster fire. 🔥🔥🔥
Benjamin Day
www.benday.com | @benday

## Slide 2: Benjamin Day
Brookline, MA
Consultant & Trainer
Rental Chief Technology Officer
Therapist for Teams
Scrum, DevOps, Azure, Team Foundation Server, Software Architecture & Testing
Microsoft MVP
Pluralsight Author
Scrum.org Trainer
@benday

## Slide 3: Implementing Scrum with Azure DevOps New!

## Slide 4: Azure DevOps Services Fundamentals Scrum Master Skills

## Slide 5: Azure DevOps Utilities (azdoutil) https://github.com/ benday-inc/azdoutil Free!

## Slide 6: On with the show.

## Slide 7
Failing project
Troubled project
At-risk project
Something ain’t right.

## Slide 8
Perception
  Credibility problems
  Customers or management thinks the project is in trouble
  Team is in trouble
  Suspicion
Reality
  Technical team thinks it’s going poorly
  Team isn’t sure it can be done
Two types of ‘fail’

## Slide 9: Perception vs. Reality
Technical Issues
People / Expectation Management Problems

## Slide 10
1-2-4-All
What causes projects to get into trouble?
Why do projects fail?
Troubled Projects
12 minutes

## Slide 11
Nothing getting done
Buggy or low quality
Unhappy stakeholders
Wobbly requirements
No idea when you’ll be done
  No data
Perception problems
Trust problems
Credibility problems
Causes of Troubled Projects

## Slide 12
At the core…
Someone thinks that their “needs” aren’t going to be met
  They’re afraid
Answer: address the fear
  Or acknowledge the fear
  Or confirm the fear
People / Expectation Management Problems

## Slide 13
The team isn’t sure it can/will be done
No progress
Exploding technical risk
Answer:
  Minimize work in progress (WIP)
  Focus on Done
  Simplify and/or fix the technical problems
  DevOps practices
Technical Issues

## Slide 14: How we talk is how we think.

## Slide 15: Words matter.

## Slide 16: When you’re trying to fix a project, talk about what you’re going to do rather than stop doing.

## Slide 17: Create motion. Communicate with motion.

## Slide 18: Steps to fix it

## Slide 19: When you’re in a hole, stop digging.

## Slide 20
Consider killing the project
Stop making promises about dates
Define what Done means
Figure out what the top priority items are for the next 2 to 4 sprints
Minimize Work In Progress (WIP)
Flow Metrics
TO DO

## Slide 21
Consider killing the project
Stop making promises about dates
Define what Done means
Figure out what the top priority items are for the next 2 to 4 sprints
Minimize Work In Progress (WIP)
Flow Metrics
Things to do

## Slide 22
Consider killing the project
Stop making promises about dates
Define what Done means
Figure out what the top priority items are for the next 2 to 4 sprints
Minimize Work In Progress (WIP)
Start using Sprint Goals
Focus on delivering to Done
  Verify you have the right people on the team
  Hold the team accountable as a unit
Backlog refinement
Consider Scrum, Kanban, and/or Flow Metrics
Automated builds, tests, and releases
TO DO

## Slide 23
Not going well?
Unhappy customers?
Not getting anything done?
Stuff you’re building is garbage?
Maybe you should just quit.
  Kill the project
  Or maybe even quit your job
Consider that the project is perhaps not worth saving
Step 1a:
Consider Killing the Project

## Slide 24
Power move
Reframe / reconfirm that it’s worth doing
Why do you want this thing?
How will you know if it’s successful?
How will you know if it’s failed?
What are your top priority features?
  Helps to focus on what’s important
Step 1b: Confirm that it’s worth continuing

## Slide 25
“When am I going to get my stuff?”
Everyone wants to know this
Nothing makes customers more nervous than when you keep making promises on dates…
…and you keep missing those dates
They think you don’t know what you’re doing
  …and they’re probably not wrong
Step 2: Stop Making Promises on Dates

## Slide 26: Stop making promises you aren’t sure you can keep. You need better data.

## Slide 27
Why are your estimates wrong?
Complexity
Unknowns
Dependencies
Wishful thinking
Why are dates slipping?

## Slide 28: The Dirty Little Huge Secret: Your customers don’t really care about your estimates.

## Slide 29: Your customers just want their done, working software.

## Slide 30: Start making your customer(s) happy.

## Slide 31: Give them something that’s done.

## Slide 32: Train them that they’ll get chunks of ‘Done’ on a regular basis.

## Slide 33
Consider killing the project
Stop making promises about dates
Define what Done means
Figure out what the top priority items are for the next 2 to 4 sprints
Minimize Work In Progress (WIP)
Start using Sprint Goals
Focus on delivering to Done
  Verify you have the right people on the team
  Hold the team accountable as a unit
Backlog refinement
Consider Scrum, Kanban, and/or Flow Metrics
Automated builds, tests, and releases
TO DO

## Slide 34
#1: Unclear definition of “Done”
#2: Not focusing on Done / Too Much Work in Progress (WIP)
#3: Product Backlog Problems
Top Reasons that projects get into trouble ($0.02)

## Slide 35
Create a Definition of Done (DoD)
Everything it takes to call a requirement done
  100% done
  “Potentially shippable”
  No more additional work required
Write it down!
Discuss it regularly
Consider sharing it with your bosses, customers, & stakeholders
  They might not understand it
  They might have suggestions
Step #3: Define ‘Done’

## Slide 36: There’s a lot more to your DoD than “the code compiles and is checked in.”

## Slide 37: Sample Definition of Done (DoD)
Development / Coder
Code is written with unit tests
Unit tests have a minimum of 75% code coverage
Code has been merged to Main
Code compiles and unit tests pass when run as part of an automated build
Database schema objects are checked in to version control
Database upgrade script is written and in version control
Code reviewed by someone other than the original author
Testing, Deployment, Ops
Written QA test plan
Tested with QA test plan by someone other than the original author
Deployed and tested in Staging environment
Automated UI tests are written and pass
No Severity 1 or 2 bugs
Reviewed by Product Owner
Passes acceptance criteria for the PBI
Known deployment & rollback plan
Deployment plan reviewed by Ops
Database changes reviewed by DBAs
Load tested
Deployed to Production

## Slide 38
Estimation
Forecasting
Work in Progress
Team communication
Communication with stakeholders
QA Testing / Defect Tracking
DevOps
Version Control / Branching & Merging
Definition of Done touches everything

## Slide 39
Your team creates it’s Definition of Done
Now your team knows if something is Done
This also mean they know when something is NOT done
  Hint: most of the time, stuff isn’t Done
Your stakeholders, customers, bosses now understand what you mean when you say ‘Done’
DoD  Transparency

## Slide 40
It’s a lot of work to get to ‘Done’
If you ship features that aren’t 100% done, your customers think you’re shipping garbage.
Your customers DO NOT UNDERSTAND the difference between ‘partially done’ and ‘done’
  Creates a horrible credibility problem
  Makes communication about status INSANELY hard
Most of the time, stuff isn’t ‘Done’

## Slide 41
Another way of saying this…
Prioritize your work
Make it clear what the priorities are
Step #4: Fix your Product Backlog

## Slide 42
List of requirements
Product Backlog represents the vision for the features and priorities for the product
Product Backlog Item = feature / requirement
Product Backlog

## Slide 43
Not enough backlog
Unclear definition of what the Product is
  (…and what it ISN’T)
Unclear understanding of “Ready” product backlog
PBIs only make sense to tech people
  Doesn’t tell a story
  Not readable by mere mortals
  Task-y PBIs
  No acceptance criteria
Product Backlog Problems

## Slide 44: You want your customers to be clear what you’re working on and why.

## Slide 45
So…uhhh…what are you working on?

## Slide 46
So…uhhh…what are you working on?
Blah blah blah sql server blah blah reactive blah blah cloud deploy blah blah blah security blah blah stuff

## Slide 47
So…uhhh…what are you working on?
Name | Size
Update payment system to convert USD to Bitcoin | 8
Fix layout and click problems on Safari on iPhone 6 | 3
Update payment system to support ApplePay | 5
Request PDF receipt delivered by email for past purchase | 2
Generate report to see orders by payment type | 3
Update payment system to take PayPal payments | 5
Mark transaction for fraud audit | 8
Upgrade site layout to support Internet Explorer 11 | 8
Refund in-store mobile purchase from administrator device | 5
Fix bugs related to jQuery upgrade (Defect #123, #456, #321, etc.) | 3
Fix bugs related to declined transactions using debit cards (Defect #132, #821) | 3
Book pre-paid appointment | 2
Request PDF summary of all purchases for date range | 3
Redeem gift card for in-store purchase | 2
Redeem gift card for mobile purchase | 3
Update public-facing website to use new logo and color scheme | 5
Update paid-user website to use new logo and color scheme | 3
Update Android app to use new logo and color scheme | 2
Update iOS app to use new logo and color scheme | 1
Real-time in-store purchase notification for managers on mobile admin app | 5
Request printed receipt after in-store mobile purchase | 5
Feature XYZ | 13
Feature ABC | 13
Use mobile camera to scan UPC and do a price comparison | 21
Create a lasting world peace | 21
Feature QWERTY | 21
Reporting dashboard for iOS & Android | 40
Federated Identity using external authentication providers | 40
Add membership card to Apple Wallet | 13
Use mobile camera to scan UPC for product and add to cart for in-store purchase | 8
Complete in-store mobile purchase | 8
Teach cats to do tax preparation | 80
RFID-based inventory control system | 80
Migrate application hosting to external cloud provider | 40
Talking unicorns | 120
This.
BOOOOOOM!!!!

## Slide 48: Step 5: Minimize Work in Progress
Do less at once to do more overall.

## Slide 49: Productivity vs. Waste
"Quality Software Management: Vol. 1 System Thinking“, Gerald Weinberg (1992), Page 284
Chart: 
| 1 Task | 2 Tasks | 3 Tasks | 4 Tasks | 5 Tasks
Task A | 1 | 0.4 | 0.2 | 0.1 | 0.05
Task B | 0 | 0.4 | 0.2 | 0.1 | 0.05
Task C | 0 | 0 | 0.2 | 0.1 | 0.05
Task D | 0 | 0 | 0 | 0.1 | 0.05
Task E | 0 | 0 | 0 | 0 | 0.05
Waste | 0 | 0.2 | 0.4 | 0.6 | 0.75

## Slide 50: Visualize Your Progress: Scrum Board
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A
Product Backlog Items
Tasks

## Slide 51: Scrum Board for the Sprint
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A
Product Backlog Item A Status
Product Backlog Item B Status
Product Backlog Item C Status

## Slide 52: Scrum Board for the Sprint
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 53: Scrum Board for the Sprint
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 54: Scrum Board for the Sprint
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 55: Scrum Board for the Sprint
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 56: Scrum Board Danger
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 57: Why is that so dangerous?

## Slide 58: Too much work in progress.

## Slide 59: ‘Work In Progress’ commonly abbreviated as ‘WIP’.

## Slide 60: Scrum Board Danger
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 61: Sprint: Day 1 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 62: Sprint: Day 2 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 63: Sprint: Day 3 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 64: Sprint: Day 4 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 65: Sprint: Day 5 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 66: Sprint: Day 6 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 67: Sprint: Day 7 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 68: Sprint: Day 8 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 69: Sprint: Day 9 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 70: Sprint: Day 10 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 71: Sprint: Day 11 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 72: Sprint: Day 12 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 73: Sprint: Day 13 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 74: Sprint: Day 14 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 75: Sprint: Day 15 of 15 (in your dreams)
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 76: Sprint: Day 14 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 77: Sprint: Day 15 of 15 (in reality)
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A
Plenty left to do

## Slide 78: What went wrong?

## Slide 79: Too much WIP. Not enough Done.

## Slide 80: Most of the Sprint Looked like This
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A
Lots of Work In Progress
0.00 Items are Done
0.00 PBIs are Done

## Slide 81: A Better Approach to WIP
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 82: A Better Approach to WIP
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 83: Huge Benefit: Risk Management

## Slide 84: Sprint: Day 5 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 85: Sprint: Day 10 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 86: Sprint: Day 13 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 87: Sprint: Day 14 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 88: Sprint: Day 15 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A

## Slide 89: Where’s the good news in that?

## Slide 90: Sprint: Day 15 of 15
 | TO DO | IN PROGRESS | DONE
PBI C
PBI B
PBI A
At least you got one PBI done.

## Slide 91: Do less at once  Decreased risk of delivering nothing in this Sprint

## Slide 92: Doing less at once != Doing less overall

## Slide 93: Same pile of work. Different way of delivering it.

## Slide 94: Whole team is going to work on one PBI as a team.

## Slide 95: Helps team to focus.

## Slide 96: Team’s focus is on details of a single PBI rather than details of a bunch of PBIs.

## Slide 97: Step 6: Flow Metrics Where’s my stuff?
Predict the future. Change the conversation. Save the world.

## Slide 98: When am I going to get my stuff?

## Slide 99
https://nday.be/go/02321

## Slide 100: Ever tried to talk about your customer about Story Points & Velocity?

## Slide 101: Traditional Scrum & Agile metrics are hard to explain…and almost impossible to understand.

## Slide 102: Story Points and Velocity don’t do a good job explaining our level of confidence.

## Slide 103: Oh…and estimation sucks.

## Slide 104: Predict the future with how you did in the past.

## Slide 106
Dr. John Little
Average Cycle Time = Average Work In Progress / Average Throughput
Little’s Law

## Slide 107
Amount of work items completed per unit of time
Measure of how fast items depart a process
Throughput

## Slide 108
Amount of elapsed time that a work item spends as Work In Progress (WIP)
Cycle Time

## Slide 109: “…the more things that you work on at any given time, the longer it is going to take for each of those things to finish.”
Daniel Vacanti Actionable Agile Metrics for Predictability
Page 46

## Slide 110: “In order to get stuff done faster, you need to work on less.”
Daniel Vacanti Actionable Agile Metrics for Predictability
Page 46

## Slide 111
Using AzdoUtil & Azure DevOps
https://github.com/benday-inc/azdoutil
Get our team’s Throughput
Forecast delivery of X items
Forecast delivery in X weeks
Forecast delivery of an item in the backlog

## Slide 112
Throughput History
Week # | Weekly Throughput / Number of PBIs Done
1 | 5
2 | 8
3 | 3
4 | 7
5 | 6

## Slide 113
Create 1,000 random simulations of how the next 5 weeks could go
  Using historical throughput
Count the most likely results
  50% confidence
  80% confidence
How much can we get done in 5 weeks?

## Slide 114
Simulation of the next 5 weeks: #1 of 1,000
Simulated Week # | Simulated Weekly Throughput / Number of PBIs Done
6 | 7
7 | 5
8 | 3
9 | 8
10 | 5
Total Throughput | 28

## Slide 115: …do that 999 more times.

## Slide 118: Forecast items in 5 weeks

## Slide 119: Forecast items in 5 weeks

## Slide 120: Step 7: I use Scrum. Now where’s my stuff?
Predicting the future for fun and profit.

## Slide 121: “Where’s my stuff?”

## Slide 122: 1) When will I get Product Backlog Item X?

## Slide 123: 2) How much done stuff will I have by Y date?

## Slide 124: Product Backlog Forecasting
Name | Size
Update payment system to convert USD to Bitcoin | 8
Fix layout and click problems on Safari on iPhone 6 | 3
Update payment system to support ApplePay | 5
Request PDF receipt delivered by email for past purchase | 2
Generate report to see orders by payment type | 3
Update payment system to take PayPal payments | 5
Mark transaction for fraud audit | 8
Upgrade site layout to support Internet Explorer 11 | 8
Refund in-store mobile purchase from administrator device | 5
Fix bugs related to jQuery upgrade (Defect #123, #456, #321, etc.) | 3
Fix bugs related to declined transactions using debit cards (Defect #132, #821) | 3
Book pre-paid appointment | 2
Request PDF summary of all purchases for date range | 3
Redeem gift card for in-store purchase | 2
Redeem gift card for mobile purchase | 3
Update public-facing website to use new logo and color scheme | 5
Update paid-user website to use new logo and color scheme | 3
Update Android app to use new logo and color scheme | 2
Update iOS app to use new logo and color scheme | 1
Real-time in-store purchase notification for managers on mobile admin app | 5
Request printed receipt after in-store mobile purchase | 5
Feature XYZ | 13
Feature ABC | 13
Use mobile camera to scan UPC and do a price comparison | 21
Create a lasting world peace | 21
Feature QWERTY | 21
Reporting dashboard for iOS & Android | 40
Federated Identity using external authentication providers | 40
Add membership card to Apple Wallet | 13
Use mobile camera to scan UPC for product and add to cart for in-store purchase | 8
Complete in-store mobile purchase | 8
Teach cats to do tax preparation | 80
RFID-based inventory control system | 80
Migrate application hosting to external cloud provider | 40
Talking unicorns | 120
Sprint 1
Sprint 2
Sprint 3
Sprint 4
? Sprint 5 ?
? Sprint 6 ?
? Sprint 7 ?
? Sprint 8 ?
? Sprint 9+ ?
Question: When does “Update Android app to use new logo and color scheme” get done?
Average Velocity = 21
 Group PBIs into groups that total to 21
Sprint Length = 2 weeks
PBI probably gets done in Sprint 4
4 sprints * 2 weeks
The Forecast for that PBI: It’s done at the end of 8 weeks

## Slide 125: Product Backlog Forecasting
Name | Size
Update payment system to convert USD to Bitcoin | 8
Fix layout and click problems on Safari on iPhone 6 | 3
Update payment system to support ApplePay | 5
Request PDF receipt delivered by email for past purchase | 2
Generate report to see orders by payment type | 3
Update payment system to take PayPal payments | 5
Mark transaction for fraud audit | 8
Upgrade site layout to support Internet Explorer 11 | 8
Refund in-store mobile purchase from administrator device | 5
Fix bugs related to jQuery upgrade (Defect #123, #456, #321, etc.) | 3
Fix bugs related to declined transactions using debit cards (Defect #132, #821) | 3
Book pre-paid appointment | 2
Request PDF summary of all purchases for date range | 3
Redeem gift card for in-store purchase | 2
Redeem gift card for mobile purchase | 3
Update public-facing website to use new logo and color scheme | 5
Update paid-user website to use new logo and color scheme | 3
Update Android app to use new logo and color scheme | 2
Update iOS app to use new logo and color scheme | 1
Real-time in-store purchase notification for managers on mobile admin app | 5
Request printed receipt after in-store mobile purchase | 5
Feature XYZ | 13
Feature ABC | 13
Use mobile camera to scan UPC and do a price comparison | 21
Create a lasting world peace | 21
Feature QWERTY | 21
Reporting dashboard for iOS & Android | 40
Federated Identity using external authentication providers | 40
Add membership card to Apple Wallet | 13
Use mobile camera to scan UPC for product and add to cart for in-store purchase | 8
Complete in-store mobile purchase | 8
Teach cats to do tax preparation | 80
RFID-based inventory control system | 80
Migrate application hosting to external cloud provider | 40
Talking unicorns | 120
Sprint 1
Sprint 2
Sprint 3
Sprint 4
? Sprint 5 ?
? Sprint 6 ?
? Sprint 7 ?
? Sprint 8 ?
? Sprint 9+ ?
Question: What can we ship at the end of 60 days?
Average Velocity = 21
Sprint Length = 3 weeks (21 days)
60 days = ~ 2.85 sprints
That’s somewhere inside of Sprint 3
(Hint: There isn’t a perfect answer.)
The 60 Day Forecast:
Sprint 1 & Sprint 2 is highly likely. Probably some of Sprint 3, too.

## Slide 126: Reminder: Both of these ‘tricks’ require 1) a known velocity and 2) a ready product backlog.

## Slide 127: New “high priority” items

## Slide 128
“I’VE GOTTA HAVE THIS!!!!”
“I NEED THIS BUG FIXED!!!”
“I WANT THAT BUTTON TO BE ORANGE!!!”
Say yes
Open your backlog
”Here’s our current priority.”
“What do you think we should bump?”
Enlist them in solving the problem
Don’t assume it’s your problem alone to solve
New, high-priority requirement?

## Slide 129: Summary

## Slide 130
Consider killing the project
Stop making promises about dates
Define what Done means
Figure out what the top priority items are for the next 2 to 4 sprints
Minimize Work In Progress (WIP)
Start using Sprint Goals
Focus on delivering to Done
  Verify you have the right people on the team
  Hold the team accountable as a unit
Backlog refinement
Consider Scrum, Kanban, and/or Flow Metrics
Automated builds, tests, and releases
TO DO

## Slide 131: Any last questions?

## Slide 132: Thank you.
www.benday.com | benday@benday.com

## Slide 133: Sprint Goals
Tell stories with your Sprints

## Slide 134: Humans like to tell stories.

## Slide 135: Stories are part of our cultures.

## Slide 136: It’s part of how we think.

## Slide 137: It’s part of how we pass on knowledge.

## Slide 138: It’s part of how we organize ourselves to get things done.

## Slide 139: Stories help us to describe goals.

## Slide 140: Without a clear goal, stuff gets fuzzy.

## Slide 141: In Scrum, we can use story telling to our advantage.

## Slide 142: Our goal at the end of every Sprint is to deliver done, working software.

## Slide 143: That’s vague. Our goal is to make software?

## Slide 144: That doesn’t have m

## Slide 145: During Sprint Planning, the team chooses some combination of PBIs in order to turn those PBIs into done, working software.

## Slide 146: On a lot of teams, the idea is “pick a bunch of PBIs then go work on them.”

## Slide 147: There’s not much of a coherent theme or story to “pick a bunch of PBIs then go work on them.”

## Slide 148: No story  tough to get focused.

## Slide 149: No story  Sprint PBIs are just a list

## Slide 150: Without a story, as Scrum Master, you’ll be stuck “herding cats”.

## Slide 151: If those PBIs make sense together, it’s easier to motivate people.

## Slide 152: If those PBIs make sense together, it’s easier to motivate people for people to be self-motivated.

## Slide 153: With a clear goal, people pull together.

## Slide 154: With a clear goal, people easily understand the mission.

## Slide 155: Not clear?

## Slide 156: Let’s use Star Wars Episode IV as an example.

## Slide 157: It’s the first Star Wars movie and a bunch of stuff happens.

## Slide 158: Let’s describe it as a list of stuff that has to be done.

## Slide 159: Star Wars: The ‘To Do’ List
Buy some used droids
Oil bath for C3PO
Pick up a package from Ben Kenobi
Sell the speeder
Get a drink at the bar at Mos Eisley
Fix the hyper-drive
Take an X-wing out for a spin
Get a medal & take a goofy picture
“What’s this movie about?”
“That sounds boring.”
A ‘to do’ list is an uninspiring goal.

## Slide 160: Here’s a better goal…

## Slide 161: “Rescue the Princess & blow up the Death Star.”

## Slide 162: “Rescue the Princess & blow up the Death Star.”
Easily understood
Leaves it to the team to figure it how
New information?  Adjust & try a new way
Just get it done
Self-organize
Motivation is clear
Much stronger sense of accomplishment than “I got my ‘to do’ list done.”

## Slide 163: The sense of accomplishment helps motivate the team for next time.

## Slide 164: Sprint Goal.

## Slide 165: A Sprint Goal is a short statement of purpose for the Sprint.

## Slide 166: Sprint Backlog: No Goal
Product Backlog Item (PBI)
Update payment system to convert USD to Bitcoin
Fix layout and click problems on Safari on iPhone 6
Upgrade site layout to support Internet Explorer 11
Update payment system to support ApplePay
Update payment system to take PayPal payments
Generate report to see orders by payment type
Request PDF receipt delivered by email for past purchase
Mark transaction for fraud audit
Implied Goal: “Get those all done”

## Slide 167: Sprint Backlog: Clear Goal
Product Backlog Item (PBI)
Update payment system to convert USD to Bitcoin
Fix layout and click problems on Safari on iPhone 6
Upgrade site layout to support Internet Explorer 11
Update payment system to support ApplePay
Update payment system to take PayPal payments
Generate report to see orders by payment type
Request PDF receipt delivered by email for past purchase
Mark transaction for fraud audit
Goal: Add new payment types to payment system & fix lingering layout issues.

## Slide 168: Sprint Backlog: Clear Goal  “Do these fit?”
Product Backlog Item (PBI)
Update payment system to convert USD to Bitcoin
Fix layout and click problems on Safari on iPhone 6
Upgrade site layout to support Internet Explorer 11
Update payment system to support ApplePay
Update payment system to take PayPal payments
Generate report to see orders by payment type
Request PDF receipt delivered by email for past purchase
Mark transaction for fraud audit
Goal: Add new payment types to payment system & fix lingering layout issues.

## Slide 169: Help your team to organize. Create a Sprint Goal.